## Sheet1
CHP/LOG County Projects
Award Dates: 02/20/20 to 02/28/23
2021-01-04
PID | COUNTY ROUTE SECTION | PRIMARY WORK CATEGORY | DESCRIPTION | PROJECT TERMINI | SALE DATE CURRENT | AWARD DATE CURRENT | AWARD DATE ACTUAL | EST. END CONSTRUCTION DATE | PROJECTED CONSTRUCTION COSTS
99757 | LOG CR 21 1.00 | Bridge Preservation | Replace the existing bridge on a new alignment allowing existing bridge to remain. | Br. No. LOG-CR 21-0100; SFN 4631838 | 2020-02-13 | 2020-02-20 | 2020-02-20 | 2024-11-15 | AWARD $1,838,031.93
108054 | D07 Sign FY20 | Traffic Control (Safety) | Project to replace deficient guide signs at various locations in Montgomery, Miami, & Clark County. In addition, wrong way signs will be placed at various interchanges throughout the district. | District wide | 2020-05-21 | 2020-05-29 | 2020-05-29 | 2021-06-30 | AWARD $1,517,525.00
101175 | LOG US 33 15.67 | Roadway Minor Rehab | Microsurface US 33 in Logan County. | LOG US 33 SLM 15.67 to 21.52 | 2020-12-17 | 2020-12-28 | 2020-12-23 | 2021-07-15 | AWARD $1,608,278.49
109332 | LOG ODNR Indian Lake State Park | Parks | ODNR project to resurface Indian Lake State Park campground | Indian Lake State Park Campground | 2021-01-14 | 2021-01-25 |  | 2021-06-30 | 860065.44
109708 | D07-CHIP-FY21 (B) | Pavement Maintenance | Chip seal various routes in D7 | Various routes in D7 (Counties: CHP, LOG, MIA) | 2021-02-11 | 2021-02-22 |  | 2021-09-30 | 676155.62
113075 | LOG-CS-FY2021 | Pavement Maintenance | Crack seal various routes within Logan County | Various routes in LOG county | 2021-02-11 | 2021-02-22 |  | 2021-07-16 | 181832.64
102321 | LOG-CR VAR GR FY 2021 | Guardrail / Roadside Maintenance | Install new guardrail and upgrade existing guardrail and end treatments on various county roads. | Various county roads in Logan County | 2020-01-20 | 2021-03-02 |  | 2021-11-30 | 312516.62
104893 | CHP 36/29 15.05/21.07 | Roadway Minor Rehab | Pavement planing and resurfacing of US 36 and SR 29 within the City of Urbana.USR 36 from Locust Street (SLM 15.05) to Berwick (SLM 16.25) - SR 29 from SLM 21.07 to 21.17 | US 36 SLM 15.05 to 16.25 and SR 29 SLM 21.07 to 21.17 | 2021-02-25 | 2021-03-08 |  | 2021-09-30 | 597943.92
107427 | CHP-29/296-10.08/0.00 | Roadway Minor Rehab | AC Overlay | CHP-29 SLM 10.08 to 15.72 - CHP-29 SLM 15.72 to 18.55 - CHP-296 SLM 0.00 to 10.52 | 2021-02-25 | 2021-03-08 |  | 2021-07-01 | 3742105.14
110821 | CHP Urbana Wildlife Area CHIP | Pavement Maintenance | ODNR Roadway Maintenance Program project to Chip Seal the Urbana Wildlife Area. | Urbana Wildlife Area | 2021-05-13 | 2021-05-24 |  | 2021-08-30 | 52800
103822 | LOG-33-15.96/20.80 | Bridge Preservation | Bridge repair. LOG-33-20.80 L - Place new LMC wearing surface using hydrodemolition. Replace torn expansion joint strip seals. Refurbish and reset abutment bearings. Patch or reface parapets. Repair abutment spalling. LOG-33-20.80 R - Place new LMC we aring surface using hydrodemolition. Investigate/evaluate expansion joint strip seals (Silicoflex installed 2016) for replacement. Investigate refurbishing and resetting abutment bearings. Patch or reface parapets. Epoxy inject abutment vertical crack s. LOG-33-15.96 R - Latex Modified Concrete wearing surface overlay to deck using hydro demolition. Patch along expansion joint using LMC when doing overlay. Seal parapet walls. Reset out of adjustment bearings. Investigate epoxy injection for abutmen t walls. Patch pier column spalling using SCC and anodes. | LOG-33-20.80 L/R - SFN 4600908/4600916 - LOG-33-15.96 R - SFN 4600835 | 2021-05-13 | 2021-05-24 |  | 2022-09-30 | 1437141.1
105901 | LOG SR 540 0.10 | Roadway Minor Rehab | Mill the existing pavement and replace with asphalt concrete, place pavement markings, pavement repair, and RPMs.Project is an Urban Paving Project. | SR 540 SLM 0.10 to SLM 1.59 | 2021-06-17 | 2021-06-28 |  | 2021-10-15 | 396000
113295 | CHP ODNR Kiser Lake State Park 2 | Parks | ODNR project in Kiser Lake State Park for resurfacing | Kiser Lake State Park | 2021-07-15 | 2021-07-26 |  | 2021-09-30 | 39600
109333 | CHP ODNR Kiser Lake State Park | Parks | ODNR project in Kiser Lake State Park for Culvert Lining | Kiser Lake State Park | 2021-10-14 | 2021-10-25 |  | 2022-06-15 | 26400
113074 | D07-PAVE-FY22 | Pavement Maintenance | Perform concrete pavement repairs on various roadways within the district. Ready to pave project. | Various routes in CLA-CHP-LOG counties | 2021-10-28 | 2021-11-08 |  | 2022-07-01 | 750000
107462 | D07 CHIP FY22 | Roadway Minor Rehab | Chip seal | Various routes in AUG,CHP, CLA & SHE counties | 2021-12-02 | 2021-12-13 |  | 2022-09-15 | 1357168
107442 | CHP-161-0.00 | Roadway Minor Rehab | AC overly with repairs | CHP SR 161 SLM 0.00 to 7.10 | 2021-12-16 | 2021-12-27 |  | 2023-07-31 | 2067520
110591 | LOG-PAVE-FY2022 | Roadway Minor Rehab | Resurfacing existing roadway with asphalt concrete. Curb ramps in DeGraff. | LOG-508-0.00 to 1.29 - LOG-274-11.02 to 12.24 - LOG-235-4.76 to 6.08 | 2022-01-13 | 2022-01-24 |  | 2000-08-31 | 1352982
109783 | CHP-PAVE-FY22 | Roadway Minor Rehab | Resurface the existing roadway with asphalt concrete (2.00"). | US36 SLM 17.27 to 19.48 - SR 235 SLM 12.59 to 16.12 - SR560 SLM 0.00 to 2.76 | 2022-01-27 | 2022-02-07 |  | 2022-09-30 | 2278896
103819 | CHP-BH-FY22 | Bridge Preservation | Bridge RepairCHP-29-2582: replace deck edges, wingwalls, resurface abutments, encase piers.CHP-54-4.18: Remove asphalt wearing surface and waterproofing. Place SDC overlay using hydrodemolition. Fix erosion along deck ends and coat exposed floor reinf orcing steel with zinc paint. Reface abutments with anodes, encase piers and rebuild deck corners and wing walls.CHP 187-02.55: deck overly, patching/refacing/encasement to the substructure. | CHP-29-25.82 - SFN 110548, CHP 54-04.18 - SFN 1101323, CHP-187-0255 - SFN 1102281 | 2022-02-17 | 2022-02-28 |  | 2022-09-30 | 550000
105411 | CHP/SHE VAR/VAR | Bridge Preservation | Project to overlay various structures using hydrodemolition and various repairs to the substructure units in Champaign and Shelby Counties | CHP-29-0264 - SFN 1100254 - CHP-245-04.03 - SFN 1102435 - CHP-560-0541 - SFN 1103369 - SHE-589-01.62 - SFN 7503210 | 2022-03-03 | 2022-03-14 |  | 2022-09-30 | 875000
99855 | LOG SR 287/VAR 00.68/VAR | Bridge Preservation | LOG-287-0068, SFN 4602730 over Macochee Crk - Rebuild deck edges with anodes. Remove and replace asphalt wearing surface and waterproofing. Reface abutment walls (no anodes). Encase pier columns, rebuild wingwalls and seal concrete work.LOG-287-0885, S FN 4602889 over Little Darby - Rebuild deck edges with anodes. Remove and replace asphalt wearing surface and waterproofing. Reface abutment walls (no anodes). Encase pier columns, rebuilds wingwalls, seal concrete work and patch pier cap with SCC.LOG- 368-0075, SFN 463486 over S. Fork Miami Rvr - Rebuild deck edges with anodes. Encase pier columns and seal concrete work.On LOG-292-16.27 - Remove all asphalt and place new SDC overlay using hydrodemolition. New deck edge on left side. Patch abutment w alls with SCC no anodes. Encase Pier columns. Rebuild wingwalls. Fix minor slope erosion. | Br. Np. LOG-287-0068/Br. No. LOG-287-0885/Br. No. LOG-368-0075/Br. No. LOG-292-16.27 | 2022-03-17 | 2022-03-28 |  | 2022-08-01 | 526700
101155 | LOG US 33 25.60 | Roadway Minor Rehab | Mill and fill the existing pavement on US 33 in Logan County with Asphalt Concrete and perform pavement repairs. | LOG US 33 SLM 25.60 to 29.65 | 2022-03-31 | 2022-04-11 |  | 2022-09-30 | 3022839
110472 | LOG-47/235-5.23/8.18 | Intersection Improvement (Safety) | Project to improve the safety and operation of the intersection of SR 47 and SR 235 | Intersection of SR 47 and SR 235 | 2022-03-31 | 2022-04-11 |  | 2022-09-30 | 1850000
104834 | LOG-CR VAR PM FY2022 | Traffic Control (Safety) | Upgrade existing pavement marking | Various county roads in Logan County | 2022-03-25 | 2022-05-02 |  | 2022-09-30 | 144200
105345 | LOG-347-3.63 | Roadway Minor Rehab | AC overlay without repairs. | LOG-347 SLM 3.63 to 5.73 | 2022-05-12 | 2022-05-23 |  | 2022-08-31 | 960960
107482 | CHP-55-0.23 | Roadway Minor Rehab | AC Overlay with repairs, curb ramps | CHP SR 55 SLM 0.23 to 11.65 | 2022-05-26 | 2022-06-06 |  | 2022-09-30 | 3005312
108874 | CHP US 68 5.36 | Roadway Minor Rehab | 1 3/4" mill and fill with superpave asphalt.Urban Paving Program | 0.07 mile S of Pearce Pl (SLM 5.36 to Washington Ave (SLM 6.93) The roundabout at USR 36/68 will be omitted (SLM 6.57-6.70) | 2022-06-16 | 2022-06-27 |  | 2022-07-02 | 575000
108377 | LOG US 68 7.22 | Roadway Minor Rehab | 1 3/4" Mill and Fill with asphalt concrete in the City of Bellefontaine.Urban Paving Program | Pine Street (SLM 7.22) to Auburn Road (SLM 8.10) | 2022-06-16 | 2022-06-27 |  | 2022-07-02 | 450000
108096 | D07-BH-FY23 (B) | Bridge Preservation | Project to seal joint seams on various culvert type bridges throughout the district using "Hydro-Tite" or like material.Work similar to PID 98640. | Various locations in the district (CHP, LOG, MER, MIA, SHE) | 2022-07-01 | 2022-07-01 |  | 2022-10-31 | 136500
113608 | LOG-68-0.52 | Pedestrian Facilities | Installation of new pedestrian crosswalks at two locations within the Village of West Liberty. | SLOGUS00068**C; SLM 0.524 - 0.978 | 2022-09-15 | 2022-09-26 |  | 2022-09-27 | 92698
101105 | LOG SR 47 5.23 | Roadway Minor Rehab | AC Overlay without repairs on SR 47 in Logan County. Ensure limits correspond with Roundabout project. | LOG SR 47 SLM 5.23 to 11.72 | 2022-10-01 | 2022-10-01 |  | 2022-10-02 | 1513468
107454 | LOG-PAVE-FY23 | Roadway Minor Rehab | AC overlay without repairs. | Various routes in LOG county | 2022-10-01 | 2022-10-01 |  | 2022-10-02 | 707100
91022 | LOG US 33 21.52 | Roadway Minor Rehab | AC Overlay with repairs. | LOG US 33 SLM 21.52 to 25.60 | 2023-01-01 | 2023-01-01 |  | 2023-09-30 | 3024096
102999 | LOG-235-8.18 | Roadway Minor Rehab | Resurfacing | LOG SR 235 SLM 8.18 to 10.39 - LOG SR 235 SLM 10.39 to 13.89 - LOG SR 235 SLM 13.89 to 17.72 | 2023-01-01 | 2023-01-01 |  | 2023-01-02 | 2744728
109788 | CHP-4-0.00 | Roadway Minor Rehab | Resurface the existing roadway with asphalt concrete (2.00"). | CHP-4 SLM 0.00 to 6.97 | 2023-01-01 | 2023-01-01 |  | 2023-01-02 | 1625404
105403 | D07 BP FY23 | Bridge / Culvert Maintenance | Project to paint the structural steel on various bridges throughout the district. | Various bridges in the district (Counties: AUG, LOG, SHE) | 2023-01-01 | 2023-01-01 |  | 2023-05-17 | 723560
113894 | LOG-347-0.00 | Roadway Major Rehab | Full asphalt removal and replacement. | LOG SR 47 SLM 0.00 to 2.37 | 2023-01-01 | 2023-01-01 |  | 2023-01-02 | 4000000